## Slide 1: Project Implementation and controlling

## Slide 2: Monitoring, Evaluation and Controlling
Monitoring
Monitoring is collecting data, recording and reporting the information concerning all aspects of project managers or others in the organization wish to know.
It is a management function to guide in the intended direction and to check the performance against the predetermined plans.

## Slide 3
Evaluation
It is the systematic judgmental process for determining the relevance, efficiency, effectiveness and impact on the project performance. It is done to improve the project implementation and to improve future project planning.

## Slide 4
Controlling
It is the management function of comparing the actual achievements with the planned ones at every stage and taking necessary actions, if required to ensure the attainment of the planned goals.
It includes three step process
Monitoring+ Evaluating+ Taking necessary actions

## Slide 5
Project Control
The project is controlled by project control system.
The project control system is an arrangement that offers the project manager with details about the deviations of the project from what has planned and also recommend corrective actions needed for rectifying the deviations.
The control system help in identifying the cost over run situations and deviations from quality parameter.

## Slide 6: Types of control
Pre-control
It is initiated before the start of the activity. It detects the probable problem in advance and takes preventive , corrective actions
Go/No-go control
It takes the form of testing to make sure that certain preconditions are met before the task is undertaken. This type of control is used for specific part of the project.
Post control
It is initiated after completion of the activity. It is based on the feedback performance results.

## Slide 7
Elements of effective Project Control System
Conformity to plans and activities
Appropriate to positions and personalities
Simplicity
Accepted by the persons concerned.
Timeliness
Economy
Emphasis on critical factors
Corrective plan
Flexibility

## Slide 8
Difficulty in implementing the project control system
Human factors ( resistance to change, reluctance to display their plans )
Complex characteristics of project
Difficulties in keeping track of performance and expenditure of complex project.
Uncertainty and change
Poor control and information system.

## Slide 9
Difficulties in project control in Nepal
In Nepal cost is given prime importance which results in slippage of time and poor workmanship quality.
Reluctance to change/ adopt proper control measures by experienced personnel of the project team.
Inappropriate reporting system or partially reporting.
Personnel bias of project staff
Few project managers believe that with time problem will get automatically resolved but in actual it worsen.

## Slide 10
Where the project manager looks the several projects, there may be tendency to affect the poor performance in one project against the good performance in the other project.
Information reporting and accounting mechanisms may be misleading
Other factors like culture, norms, values of personnel, time period available, geographic location.

## Slide 11: Project control cycle
Establishing standards
Observing/ measuring Performance
Finding Deviations
Taking corrective actions

## Slide 12
Establishing standards( What to be done )
Project performance standards are based on project planning. Through the standards project is controlled. They are the standard point of control. They should be reasonable standards and can be in terms of time, quantity, quality cost etc.
Observing/ measuring performance ( What actually was done )
Actual performance is measured within a given period. It is continuous ongoing process to feedback. Suitable monitoring system is required to get required information.

## Slide 13
Finding deviations ( extent and cause of deviations )
In third steps the actual performance is compared with the standards and deviation is identified if any. The sources of the deviation is analysed.
Taking the corrective actions
After the identification of deviation, then corrective actions are taken to bring back the project on track. If the performance deviation is within allowable limit, no action will be taken. If not, they can be corrected by improvement of design: changing raw materials etc. or standards can be revised as requirement.

## Slide 14: Elements project control
Time control
The time/schedule control process monitors and controls the changes to the project schedule. Output includes
Updates of the schedule model data and baseline
Performance measurements
Requested changes
Recommend corrective actions
Updates the project management plan
Activity list and activity attribute updates

## Slide 15
Cost control
Cost control may be broadly defined as the process of controlling the expenditure in a project at all stages from the inception through its development.
Cost control means controlling the changes to project budget.
Cost control is mainly concerned with
Influencing the factors which create changes to the cost baseline to ensure that changes are beneficial.
Determining the cost baseline has changed.
Managing the actual changes as when they occur.

## Slide 16: Elements of cost control
Elements of cost control | Description
Observation | Regular observation should be made on: material consumed, manpower and equipment employed, other direct costs
Comparison | The observed data must be compared with the design standard by calculating variances
Identify the reasons for variance | If the variance is large, it is important to know the reasons for the variance. For this it is important to check the purchase price of materials, quality, wastage, work condition
Corrective action | If the variance cannot be justified then the middle level or higher level management takes the necessary action for bringing the cost of the project in to the track. It should be worked out and implemented which may include re-scheduling of the project

## Slide 17
Quality control
The quality control performances process measures specific project results to determine whether the project is meeting quality standards.
Under the quality control following things are used.
Raw materials and intermediate stage product testing
Some self inspection by operator
Lagging process performance data
Feedback process information to the operators, setters and production supervisors
Use of basic statistics
Process control

## Slide 18
Tools for quality control
Well written specification
National and international standards ( codes ) NS , ISI
Other international organization WHO UNO
Procedural guidelines
Training.

## Slide 19
Quality attributes
Performance
Features
Reliability
Serviceability
Durability
Aesthetic characteristics
Perceived quality

## Slide 20
Project schedule control
Controlling schedule is the project management activity in which the activities are compared against the schedule baseline to understand whether project is ahead of schedule or behind.
Based on the deviation you can plan on corrective or preventive actions and manage the baseline.
Schedule control involves
Determining the current status
Influencing factors that could cause schedule changes
Identify if the schedule has changed
Managing the changes as they occur.

## Slide 21: Earned Value Analysis
Earned value analysis is an approach for measuring, how much has been completed in a project at given point of time and performance
This analysis can be done by calculating how much time, the work has taken and the resources it has utilized.
These value are compared with the planned value of time and resources. If the time taken to do the particular task is greater than what was planned, it means that the project is running behind schedule. Similarly, if the resources utilized are more than what were planned, it means the project has not been managed efficiently in terms of resources.

## Slide 22
It is used as a tool for cost control as it is very helpful as it is very helpful in determining how the project is going, in terms of cost scope and time.
That is whether the cost is under control and if it will go over planned budget or in how much time the project would be completed if we continue working at same pace. w

## Slide 23: Project quality control
Quality control
Quality control is the process for monitoring specific project result to determine whether this comply with relevant quality standards and identifying ways to eliminate cause of unsatisfactory performance.
According to American society for quality (ASQ)” Quality control consist of the observation techniques and activities used to fulfill requirement for quality.”

## Slide 24
Quality Assurance
Quality assurance is a broad practice used for assuring the quality of products or service. According to ASQ quality assurance is the planned and systematic activities implemented in a quality system so that quality requirements for the product and service will be fulfilled.

## Slide 25
Quality control vs Quality assurance
Quality control is a product oriented whereas quality assurance is process oriented.
Quality control makes sure that the end product meets the quality requirement where as quality assurance makes sure that the process of the manufacturing the product does adhere to the standards.
Quality assurance can be identified as a productive process while quality control can be noted as a reactive process.

## Slide 26: Techniques of Quality control
Following techniques shall be applied for the quality control/assurance
Preparation of quality control/ assurance plan
Regular inspection/ supervision
Testing
a. Destructive test or non destructive
b. field or lab
Sampling
Identifying deviations or discrepancies
Adopting necessary corrective measures

## Slide 27
Cost of quality
Cost of quality is a combination of
Cost to control quality ( Prevention and appraisal )
Cost of failure to control quality ( Internal and external failures)
Cost of quality becomes the cost to the company of doing things wrong or not confirming the specification.

## Slide 28
Prevention cost
The cost of preventing defective work is usually extended before the product is made or service rendered. These cost include
Design reviews and drawing checks
Quality orientation program, education and training
Process control
Process orientations
Suppliers evaluation and presentation
Workers training.

## Slide 29
Appraisal cost
The cost of appraisal is incurred for auditing service procedure to make sure they conform to the prescribed work practices. These include
Process capability managements (e.g. control charts)
Tests, gauges, test equipments
Prototype inspection and tests
In process and final inspection and tests
Checking material furnished by suppliers
Work in process goods testing and inspections

## Slide 30
Internal failure costs
Internal failure costs is applicable when the product is in factory and not been sold. These cost include
Expenses for producing items that are scrapped
Redesign
Reworking and downtime
Retesting defective items
Lost value of items sold as seconds
Cost of delays
Administration time to review non conforming materials for disposition
scrap

## Slide 31
External failure costs
These cost are applicable to goods when the product has been sold. These cost include
Warranty cost
Product liability( insurance and settlements )
Consumers affairs ( dealing primarily with the customer complaints about quality )
Field service ( mostly repairs of what should have worked)
Product returns, recalls

## Slide 32: Relation between time cost and quality

## Slide 33: Project management information system ( PMIS)
It is a system of a data base for the project.
It may be defined as a system of obtaining, abstracting, storing, retrieving and analyzing data produce information for the use by the managers in planning, controlling and decision making. It consists of people, equipment and procedure. It is continuously developing in nature.
An information system includes
Policy flow from the management
Information flow to the management

## Slide 34
Objectives of PMIS
To reduce project duration
To make better use of resources
To increase resources productivity
To decrease cost/price
To bring the new facts to the knowledge
To reduce the uncertainty in decision making

## Slide 35
Advantages of PMIS
Promote the better understanding in project
It helps to target control by quantifying the risks and initiating the corrective actions
It helps to comprehend the change in the project
It provides basis to monitor, evaluate and show the interrelationship among cost. Schedule and technical performance of entire project.
It helps to identify project problem before they occur
It helps to make better decision and execution of those decisions

## Slide 36
It facilitates project planning
It informs the stakeholders about the progress and status of project.
PMIS simplifies project control
It reduces information overload in project
It facilitates project transaction such as progress payments
It targets control by quantifying the risks, testing proposed control and initiating corrective actions.